## Summary
SIT Daily Status Display Hub Development Sprint 5.1 & Sprint 5.2 |  |  |  | Day 4 | 2026-04-24
ORIGINAL |  | REVISED
Start | End | Start | End
2026-02-09 | 2026-02-13
Overall Status: | GREEN
Total TC's | PLAN TO DATE |  |  | ACTUAL EXECUTION TO DATE | [6 empty] | Actual vs Planned Executed %
| Plan Executed TC's | Execution Rate (%) | Pass Rate (%) | Executed TC's | Passed | Failed | NA | Blocked | Execution Rate (%) | Pass Rate (%)
20 | 20 | 100% | 0% | 17 | 17 | 0 | 0 | 0 | 85% | 100% | 85%
DEFECT PENETRATION
Total Defect | Penetration Rate (%) | Critical | High | Medium | Low
0 | 0% | 0 | 0 | 0 | 0
Executive Summary
Day 2 Internal Test no defect
Test Case
No | Sprint | Ticket Story |  | Module |  | Platform | Testing Start | Testing End | Total TCs | TC Run | TC Passed | TC Failed | TC NA | TC Blocked | TC Not Tested | Remark |  |  | Status
1 | Sprint 5.1 | https://snpgroup.atlassian.net/browse/SPPAT-1724 |  | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently |  | Web CMS | 2026-02-09 | 2026-02-13 | 6 | 6 | 6 | 0 | 0 | 0 | 0
2 | Sprint 5.1 | https://snpgroup.atlassian.net/browse/SPPAT-1725 |  | As an Global Admin and Super Admin, I can create Industries, Categories, and Sub-Categories data on the form field page when the data I am searching for is not found |  | Web CMS | 2026-02-09 | 2026-02-13 | 4 | 3 | 3 | 0 | 0 | 0 | 0
11 | Sprint 5.1 | https://snpgroup.atlassian.net/browse/SPPAT-1741 |  | As an Global Admin, Super Admin, PIC Organization, I can view the list of user management data so that I can monitor and manage user information effectively |  | Web CMS | 2026-02-09 | 2026-02-13 | 4 | 3 | 3 | 0 | 0 | 0 | 0
12 | Sprint 5.1 | https://snpgroup.atlassian.net/browse/SPPAT-1748 |  | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system |  | Web CMS | 2026-02-09 | 2026-02-13 | 6 | 5 | 5 | 0 | 0 | 0 | 0
[8 empty] | TOTAL | 20 | 17 | 17 | 0 | 0 | 0 | 0
[9 empty] | Total TCs | TC Run | TC Passed | TC Failed | TC NA | TC Blocked | TC Not Tested
Open Defects
No. | ID / Ticket JIRA |  | Error Description |  | Test Case | Impacted Test Cases | Severity | Status | PIC (FE/BE/Mobile) | Raised Date | ETA | Aging
NOTE
DEFECT STATUS ONLY CAN BE CLOSED UNTIL RETEST COMPLETED AND RESULT VALIDATED BY TOWER OR BUSINESS USER
Execution Details
DAY | Total TCs | 1331
| Per Day | [8 empty] | Accumulated (Total)
| Execution Date | Plan Execution | Plan Passed | Recovery Plan | Recovery Pass | Passed | Failed | NA | Blocked | Plan Execution | % Plan Execution | Plan Passed | % Plan Passed | Actual | % Actual | Passed | Failed | NA | Blocked | Remaining
1 | 2026-04-21 | 120 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 9.016% | 120 | 9.016% | 120 | 9.016% | 120 | 0 | 0 | 0 | 1211
2 | 2026-04-22 | 112 | 112 | 0 | 0 | 112 | 0 | 0 | 0 | 232 | 17.43% | 232 | 17.43% | 232 | 17.43% | 232 | 0 | 0 | 0 | 1099
3 | 2026-04-23 | 108 | 108 | 0 | 0 | 108 | 0 | 0 | 0 | 340 | 25.54% | 340 | 25.54% | 340 | 25.54% | 340 | 0 | 0 | 0 | 991
4 | 2026-04-24 | 45 | 45 | 0 | 0 | 45 | 0 | 0 | 0 | 265 | 19.91% | 265 | 19.91% | 385 | 28.93% | 385 | 0 | 0 | 0 | 946
5 | 2026-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 11.5% | 153 | 11.5% | 385 | 28.93% | 0 | 0 | 0 | 0 | 946
|  | 385 | 385 | 0 | 0 | 385 | 0 | 0 | 0
|  |  | Passed+NA= | 385
|  |  | Passed+Failed+NA= | 385
|  |  | Pass Rate= | 100%
DO NOT CHANGE THE FORMULA
PROJECT STATUS
GREEN | Execution rate and pass rate match or better than plan
AMBER | Execution rate or pass rate lower than plan
RED | Execution rate and pass rate lower than plan
END DATE STATUS (ORIGINAL/REVISED)
[DATE]
[DATE]
[DATE]
Formulas:
TC Blocked = IF(AND([End, row above]>=TODAY(),ISBLANK([Failed])=TRUE()),0,[TC Blocked, row above]+[Failed]+[NA]+[Blocked])
Remark = IF(AND([End, row above]>=TODAY(),OR(ISBLANK([Failed])=TRUE(),[Failed]=0)),0,[Remark, row above]+[Failed])
Failed = IF(AND([End, row above]>=TODAY(),OR(ISBLANK([NA])=TRUE(),[NA]=0)),0,[Failed, row above]+[NA])

## Global Admin
NO | SPRINT | TC_ID | LINK STORY | FEATURE / SUITE | ROLE USER | PLATFORM | TEST CASE | PRECONDITIONS | STEPS | DATA | EXPECTED | BEHAVIOUR | PRIORITY | SEVERITY | COMPLEXITY | TYPE | ACTUAL RESULT | REMARKS | DATE | PIC TESTER | EVIDENCE SIT | Evidence Internal Test | Automate/Manual
1 | Sprint 5.1 | TC ID - 06 | https://snpgroup.atlassian.net/browse/SPPAT-1724 | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently | Global Admin | Web CMS | Global admin can search data Product Industry | * User already login as Global Admin * User opened Product Industry page | * Input character on search column * Press button Enter from keyboard | rules : * must press enter button from keyboard * min 3 character for search * can input for example SABUN, Sabun, SAbun, sabun (not case sensitive) | * Success input character * Success show the result | Positive | High | Normal | Medium | Functional | Passed |  | 2026-04-21 | Miftha
2 | Sprint 5.1 | TC ID - 07 | https://snpgroup.atlassian.net/browse/SPPAT-1724 | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently | Global Admin | Web CMS | Global admin input character on column search less than 3 character | * Already login as Global Admin * Already on Product Industry page | * Input less than 3 character on column search * Press enter button on your keyboard | Example : * Have keyword SABUN and then input character only S or S.A on column search | Cannot search the keyword with less than 3 character and the result cannot shown | Negative | Medium | Normal | Medium | Functional | Passed |  | 2026-04-21 | Miftha
3 | Sprint 5.1 | TC ID - 08 | https://snpgroup.atlassian.net/browse/SPPAT-1724 | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently | Global Admin | Web CMS | Global Admin can filter on dropdown field | * Already login as Global Admin * Already on Product Industry page | * Click filter dropdown beside search column * Select the option based on list | * - * - | * Open the dropdown and show the list on dropdown * Success selected option and show result based on filter | Positive | High | Normal | Medium | Functional | Passed |  | 2026-04-21 | Miftha
4 | Sprint 5.1 | TC ID - 09 | https://snpgroup.atlassian.net/browse/SPPAT-1724 | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently | Global Admin | Web CMS | Global admin can't search data Product Industry | * User already login as Global Admin * User opened Product Industry page | * Input character on search column with invalid data * Press button Enter from keyboard | * example : 1@!&%&*! | * Success input character * Success show the result data not found * Success showed snackbar "Industry search term contains invalid characters" | Negative | Medium | Normal | Medium | Functional | Passed | 1@@!#$@ -> "Industry search term contains invalid characters" 1@!&%&*# -> "Internal Server Error" 1@!&%&*! -> "Internal Server Error" | 2026-04-21 | Miftha
5 | Sprint 5.1 | TC ID - 10 | https://snpgroup.atlassian.net/browse/SPPAT-1724 | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently | Global Admin | Web CMS | Global admin can view list of button elipsis on Action Column | * Already login as Global Admin * Already on Product Industry page | * Click kebab menu on Action Column |  | * Show 2 buttons, there are Edit & Delete on kebab menu | Positive | High | Normal | Medium | Functional | Passed |  | 2026-04-21 | Miftha
6 | Sprint 5.1 | TC ID - 11 | https://snpgroup.atlassian.net/browse/SPPAT-1724 | As an Global Admin, and Super Admin I can view the product industry list so that I can manage and monitor all available master data efficiently | Global Admin | Web CMS | Global Admin can filter with result data not found | * Already login as Global Admin * Already on Product Industry page | * Click filter dropdown beside search column * Select the option based on list | Data on list has been deleted before | * Open the dropdown and show the list on dropdown * Success selected option and show result data not found | Negative | Medium | Normal | Medium | Functional | Passed |  | 2026-04-21 | Miftha
7 | Sprint 5.1 | TC ID - 12 | https://snpgroup.atlassian.net/browse/SPPAT-1725 | As an Global Admin and Super Admin, I can create Industries, Categories, and Sub-Categories data on the form field page when the data I am searching for is not found | Global Admin | Web CMS | Global Admin can view and select list dropdown data "Industry, Category, Sub Category" that has been added from system (BE) on Product Industry page | * User is already login as Global Admin and accessed "Product Industry" menu * Makesure system already added data "Industry, Category, Sub Category" | * Click button "Create Product Industry +" * Click dropdown "Industry" * Select one of list dropdown "Industry" * Click dropdown "Category" * Select one of list dropdown "Category" * Click dropdown "Sub Category" * Select one of list dropdown "Sub Category" | * - * - * ex: Food & Beverages * - * ex: Asian Food * - * ex: Main Course | * Successfully display pop-up "Create Product Industry". On the pop-up display enable dropdown "Industry" (mandatory field), disable dropdown "Category" (mandatory field), disable dropdown "Sub Category" (mandatory field), textarea Product Example (non mandatory). * Successfully display list Industry from system with search bar * Successfully selected list dropdown "Industry", then display dropdown "Category" enable. * Successfully display list Category from system with search bar * Successfully selected list dropdown "Category", then display dropdown "Sub Category" enable. * Successfully display list Sub Category from system * Successfully selected list dropdown "Sub Category" | Positive | Medium | Major | Medium | Functional
8 | Sprint 5.1 | TC ID - 13 | https://snpgroup.atlassian.net/browse/SPPAT-1725 | As an Global Admin and Super Admin, I can create Industries, Categories, and Sub-Categories data on the form field page when the data I am searching for is not found | Global Admin | Web CMS | Global Admin can search data Product Industry only 3 character "Industry, Category, Sub Category" using existing data from system | * User is already login as Global Admin and accessed "Product Industry" menu * Makesure system already added data "Industry, Category, Sub Category" | * Click button "Create Product Industry +" * Click dropdown "Industry" * Type on search bar "Industry" with 3 char * Press "Enter" on keyboard * Select one of list dropdown "Industry" * Click dropdown "Category" * Type on search bar "Category" with 3 char * Press "Enter" on keyboard * Select one of list dropdown "Category" * Click dropdown "Sub Category" * Type on search bar "Category" with 3 char * Press "Enter" on keyboard * Select one of list dropdown "Sub Category" | * - * - * ex: Foo * - * ex: Food & Beverages * - * ex: Asi * - * ex: Asian Food * - * ex: Mai * - * ex: Main Course | * Successfully display pop-up "Create Product Industry". On the pop-up display enable dropdown "Industry" (mandatory field), disable dropdown "Category" (mandatory field), disable dropdown "Sub Category" (mandatory field), textarea Product Example (non mandatory). * Successfully display list Industry from system with search bar * Successfully type on search bar with 3 char * Successfully display suggestion search based on keyword * Successfully selected list dropdown "Industry", then display dropdown "Industry" enable. * Successfully display list Category from system with search bar * Successfully type on search bar with 3 char * Successfully display suggestion search based on keyword * Successfully selected list dropdown "Category", then display dropdown "Sub Category" enable. * Successfully display list Sub Category from system with search bar * Successfully type on search bar with 3 char * Successfully display suggestion search based on keyword * Successfully selected list dropdown "Sub Category" | Positive | Medium | Major | Medium | Functional | Passed |  | 2026-04-21 | Miftha
9 | Sprint 5.1 | TC ID - 14 | https://snpgroup.atlassian.net/browse/SPPAT-1725 | As an Global Admin and Super Admin, I can create Industries, Categories, and Sub-Categories data on the form field page when the data I am searching for is not found | Global Admin | Web CMS | Global Admin cannot search data Product Industry because system not found the result if search only 3 character "Industry, Category, Sub Category" on Product Industry | * User is already login as Global Admin and accessed "Product Industry" menu * Makesure system already added data "Industry, Category, Sub Category" | * Click button "Create Product Industry +" * Click dropdown "Industry" * Type on search bar "Industry" with 3 char * Press "Enter" on keyboard * Select one of list dropdown "Industry" * Click dropdown "Category" * Type on search bar "Category" with 3 char * Press "Enter" on keyboard * Select one of list dropdown "Category" * Click dropdown "Sub Category" * Type on search bar "Category" with 3 char * Press "Enter" on keyboard * Select one of list dropdown "Sub Category" | * - * - * ex: Foo * - * - * ex: Asi * - * - * - * ex: Mai * - * - | * Successfully display pop-up "Create Product Industry". On the pop-up display enable dropdown "Industry" (mandatory field), disable dropdown "Category" (mandatory field), disable dropdown "Sub Category" (mandatory field), textarea Product Example (non mandatory). * Successfully display list Industry from system with search bar * Successfully type on search bar with 3 char * Successfully display result not found and in the new line display "keyword" and button "+ Add New Data" * Successfully selected list dropdown "Industry", then display dropdown "Industry" enable. * Successfully display list Category from system with search bar * Successfully type on search bar with 3 char * Successfully display result not found and in the new line display "keyword" and button "+ Add New Data" * Successfully selected list dropdown "Category", then display dropdown "Sub Category" enable. * Successfully display list Sub Category from system with search bar * Successfully type on search bar with 3 char * Successfully display result not found and in the new line display "keyword" and button "+ Add New Data" | Negative | Medium | Major | Medium | Functional | Passed |  | 2026-04-22 | Miftha
10 | Sprint 5.1 | TC ID - 15 | https://snpgroup.atlassian.net/browse/SPPAT-1725 | As an Global Admin and Super Admin, I can create Industries, Categories, and Sub-Categories data on the form field page when the data I am searching for is not found | Global Admin | Web CMS | Global Admin cannot search data Product Industry because system not found the result if search more than 3 character "Industry, Category, Sub Category" on Product Industry | * User is already login as Global Admin and accessed "Product Industry" menu * Makesure system already added data "Industry, Category, Sub Category" | * Click button "Create Product Industry +" * Click dropdown "Industry" * Type on search bar "Industry" with more than 3 char * Press "Enter" on keyboard * Select one of list dropdown "Industry" * Click dropdown "Category" * Type on search bar "Category" with more than 3 char * Press "Enter" on keyboard * Select one of list dropdown "Category" * Click dropdown "Sub Category" * Type on search bar "Category" with more than 3 char * Press "Enter" on keyboard | * - * - * ex: Food * - * - * ex: Asia * - * - * - * ex: Main * - * - | * Successfully display pop-up "Create Product Industry". On the pop-up display enable dropdown "Industry" (mandatory field), disable dropdown "Category" (mandatory field), disable dropdown "Sub Category" (mandatory field), textarea Product Example (non mandatory). * Successfully display list Industry from system with search bar * Successfully type on search bar with more than 3 char * Successfully display result not found and in the new line display "keyword" and button "+ Add New Data" * Successfully selected list dropdown "Industry", then display dropdown "Industry" enable. * Successfully display list Category from system with search bar * Successfully type on search bar with more than 3 char * Successfully display result not found and in the new line display "keyword" and button "+ Add New Data" * Successfully selected list dropdown "Category", then display dropdown "Sub Category" enable. * Successfully display list Sub Category from system with search bar * Successfully type on search bar with more than 3 char * Successfully display result not found and in the new line display "keyword" and button "+ Add New Data" | Negative | Medium | Major | Medium | Functional | Passed |  | 2026-04-22 | Miftha
Note on G1: Shabrina Rahmah: Web, Mobile Web, Android TV, Samsung TV

## PIC Organization
NO | SPRINT | TC_ID | LINK STORY | FEATURE / SUITE | ROLE USER | PLATFORM | TEST CASE | PRECONDITIONS | STEPS | DATA | EXPECTED | BEHAVIOUR | PRIORITY | SEVERITY | COMPLEXITY | TYPE | ACTUAL RESULT | REMARKS | DATE | PIC TESTER | EVIDENCE SIT | Automate/Manual
1 | Sprint 5.1 | TC ID - 222 | https://snpgroup.atlassian.net/browse/SPPAT-1741 | As an Global Admin, Super Admin, PIC Organization, I can view the list of user management data so that I can monitor and manage user information effectively | PIC Organization | Web CMS | PIC Organization click settings button on detail Organization page | * User already login as PIC Organization | * Click "Organization Management" menu * Click 1 of Organization on the list * Click Setting icon * Hoover information icon * Click "Cancel" button | * - * - * - * - * - | * Redirect to Organization Management page * Redirect to detail Organization * Show pup up setting organization * Show information "1 Slot is 1 Minutes set your total slots, and the system multiplies them by your showtimes. Example: Insert 20 Slot x 1 Minutes = 20 Minutes campaign in 1 day" * Close pop up | Positive | Medium | Normal | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 222.mp4
2 | Sprint 5.1 | TC ID - 223 | https://snpgroup.atlassian.net/browse/SPPAT-1741 | As an Global Admin, Super Admin, PIC Organization, I can view the list of user management data so that I can monitor and manage user information effectively | PIC Organization | Web CMS | PIC Organization do Search based on Name and Email & Filter based on All Role | * User already login as PIC Organization * User already on Organization Management page. * User already on Detail Organization page. | * Search on Search bar * Delete all keyword on search bar * Click "All Status" dropdown filter * Choose 1 dropdown option | * Min 3 Char * - * PIC Organization, content creator, device operator, admin organization * PIC Organization, content creator, device operator, admin organization | * Show search filter ,based on Name and Email name. * Show all Data without any filter * Show dropdown * Show filtered based on Role Dropdown | Positive | Medium | Normal | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 223.mp4
3 | Sprint 5.1 | TC ID - 224 | https://snpgroup.atlassian.net/browse/SPPAT-1741 | As an Global Admin, Super Admin, PIC Organization, I can view the list of user management data so that I can monitor and manage user information effectively | PIC Organization | Web CMS | PIC Organization click detail organization menu, but no data is displayed yet | * User already login as PIC Organization * There is no data on Detail Organization | * Click "Organization Management" menu | * - | * 'The system will display a message: User empty. No data entry" | Negative | Medium | Normal | Medium | Functional
4 | Sprint 5.1 | TC ID - 225 | https://snpgroup.atlassian.net/browse/SPPAT-1741 | As an Global Admin, Super Admin, PIC Organization, I can view the list of user management data so that I can monitor and manage user information effectively | PIC Organization | Web CMS | PIC Organization click detail organization menu ,and search null data | * User already login as PIC Organization * User already on Detail Organization | * Search null data on searchbar | * - | * 'The system will display a message: 'Data Not Found, Data Empty" | Negative | Medium | Normal | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 225.mp4
5 | Sprint 5.1 | TC ID - 226 | https://snpgroup.atlassian.net/browse/SPPAT-1748 | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system | PIC Organization | Web CMS | PIC Organization Create user on Organization Management | * PIC Organization already login as PIC Organization * PIC Organization already on Organization Management page * PIC Organization already choose 1 organization of data list | * Click "Create User +" button * Input Fullname * Input Email * Select User Role * Input Password * Input Re-Password * Switch toggle Status User * Hoover pointer to information "i" icon * Click "Create User" button | * - * Char max 254 * Mandatory "@", Char max 254 * Content creator, Device Operator, Admin Organization * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * Min 8 Char, Max 20 Char, contain at least one uppercase letter, one number, and one special character. * On/Off * - * - | * Show Create User form * Successfully inputted to textbox * Successfully inputted to textbox * Successfully Choose the dropdown * Successfully inputted to textbox * Successfully inputted to textbox * Successfully installed the toggle status * Show information about the toggle * Successfully created the user and show snackbar "user created successfully" | Positive | High | Major | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 226.mp4
6 | Sprint 5.1 | TC ID - 227 | https://snpgroup.atlassian.net/browse/SPPAT-1748 | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system | PIC Organization | Web CMS | PIC Organization can't Create user on Organization Management if password and re-password not match | * PIC Organization already login as PIC Organization * PIC Organization already on Organization Management page * PIC Organization already choose 1 organization of data list | * Click "Create User +" button * Input Fullname * Input Email * Select User Role * Input Password * Click eye icon * Input Different Re-Password * Click eye icon | * - * Char max 254 * Mandatory "@", Char max 254 * Content creator, Device Operator, Admin Organization * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * - * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * - | * Show Create User form * Successfully inputted to textbox * Successfully inputted to textbox * Successfully Choose the dropdown * Successfully inputted to textbox * Show or hide text on textbox * the indicator turns red. * Show or hide text on textbox | Negative | High | Major | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 227.mp4
7 | Sprint 5.1 | TC ID - 228 | https://snpgroup.atlassian.net/browse/SPPAT-1748 | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system | PIC Organization | Web CMS | PIC Organization can't Create user on Organization Management when the Email already registered | * PIC Organization already login as PIC Organization * PIC Organization already on Organization Management page * PIC Organization already choose 1 organization of data list | * Click "Create User +" button * Input Fullname * Input Email that already registered * Select User Role * Input Password * Input Re-Password * Switch toggle Status User * Click "Create User" button | * - * Char max 254 * Mandatory "@", Char max 254 * Content creator, Device Operator, Admin Organization * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * On/Off * - | * Show Create User form * Successfully inputted to textbox * Successfully inputted to textbox * Successfully Choose the dropdown * Successfully inputted to textbox * Successfully inputted to textbox * Successfully installed the toggle status * System display alert snaclbar information "User with email 'userclient@gmail.com' already exists" | Negative | High | Major | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 228.mp4
8 | Sprint 5.1 | TC ID - 229 | https://snpgroup.atlassian.net/browse/SPPAT-1748 | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system | PIC Organization | Web CMS | PIC Organization can't Create user on Organization Management when lost connection | * PIC Organization already login as PIC Organization * PIC Organization already on Organization Management page * PIC Organization already choose 1 organization of data list * Not connect to internet | * Click "Create User +" button * Input Fullname * Input Email that already registered * Select User Role * Input Password * Input Re-Password * Switch toggle Status User * Click "Create User" button | * - * Char max 254 * Mandatory "@", Char max 254 * Content creator, Device Operator, Admin Organization * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * On/Off * - | * Show Create User form * Successfully inputted to textbox * Successfully inputted to textbox * Successfully Choose the dropdown * Successfully inputted to textbox * Successfully inputted to textbox * Successfully installed the toggle status * System display alert information "User created failed" | Negative | High | Major | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 229.mp4
9 | Sprint 5.1 | TC ID - 230 | https://snpgroup.atlassian.net/browse/SPPAT-1748 | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system | PIC Organization | Web CMS | PIC Organization can't Create user on Organization Management when internal server error | * PIC Organization already login as PIC Organization * PIC Organization already on Organization Management page * PIC Organization already choose 1 organization of data list * Server unavailable | * Click "Create User +" button * Input Fullname * Input Email that already registered * Select User Role * Input Password * Input Re-Password * Switch toggle Status User * Click "Create User" button | * - * Char max 254 * Mandatory "@", Char max 254 * Content creator, Device Operator, Admin Organization * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * On/Off * - | * Show Create User form * Successfully inputted to textbox * Successfully inputted to textbox * Successfully Choose the dropdown * Successfully inputted to textbox * Successfully inputted to textbox * Successfully installed the toggle status * System display alert information "User created failed" | Negative | High | Major | Medium | Functional
10 | Sprint 5.1 | TC ID - 231 | https://snpgroup.atlassian.net/browse/SPPAT-1748 | As an Global Admin, Super Admin and PIC Organization, I can create new user management data so that I can register and manage user information within the system | PIC Organization | Web CMS | PIC Organization cannot save the form when it has been closed | * PIC Organization already login as PIC Organization * PIC Organization already on Organization Management page * PIC Organization already choose 1 organization of data list | * Click "Create User +" button * Input Fullname * Input Email * Select User Role * Input Password * Input Re-Password * Switch toggle Status User * Hoover pointer to information "i" icon * Click "Cancel" button * Click "Create User +" button | * - * Char max 254 * Mandatory "@", Char max 254 * Content creator, Device Operator, Admin Organization * Min 8 Char,Max 20 Char, contain at least one uppercase letter, one number, and one special character. * Min 8 Char, Max 20 Char, contain at least one uppercase letter, one number, and one special character. * On/Off * - * - * - | * Show Create User form * Successfully inputted to textbox * Successfully inputted to textbox * Successfully Choose the dropdown * Successfully inputted to textbox * Successfully inputted to textbox * Successfully installed the toggle status * Show information about the toggle * Closed the form * . Show blank Create User form | Negative | High | Major | Medium | Functional | Passed |  | 2026-04-21 | Meriyan Dwi Prakosa | PIC Org TC ID 231.mp4
Note on G1: Shabrina Rahmah: Web, Mobile Web, Android TV, Samsung TV

## Legend
Filename | This file excel name should be [CRQ number]_[anything]
CRQ number refer to CRQ in Selena/ Remedy, anything free as necessary
sample: CRQ000000407740_VAS Code-Arief Setiawan
sheet Template Test Case | could be rename to group of test case, e.g TC Kartu Halo, TC Modul A, etc
sheet Template Defect | could be rename to group of defect, e.g Defect Kartu Halo, Defect Modul A, etc
sheet Legend | sheet that explain how to read this file
Template Test Case
Plan Execution Date | plan execution date for test case
Test Case | name of the test case, for easy reference
Description Test Case | long description of the test case
System Related | surrounding system
Step | detail step number of a test case
Step Description | description of a step of a test case
Expected Result | expected result of a test case, make it as clear as possible
Actual Execution Date | actual execution date with team testing
Status Test Case | status of this test case, choice: No Run, Hold, Invalid, Passed, Failed
Actual Result | currect result/ final result of a test case
Severity | level severity of a test case, refer to TRA/ Test Strategy of this test CRQ, choice: Critical, High, Medium, Low
Cycle | increasing number to show how many this test case have been reiterate, e.g 1, 2, 3, etc
Notes | additional notes, as necessary
Template Defect
Test Case | leave empty for now, name of the test case, for easy reference, foreign key from test case table
Step | leave empty for now, detail step number of a test case, foreign key from test case table
Severity Defect | priority of the defect, choice: Critical, Very High, High, Medium, Low
Defect Description | description of the defect
Status Defect | status of the defect, choice: New, Open, Deferred, Rejected, Closed
Notes | additional notes, optional
#REF!